## Cover
TEST CASE
Project Name | <Project Name> |  |  | Creator
Project Code | <Project Code> |  |  | Reviewer/Approver
Document Code | <Project Code>_XXX_vx.x |  |  | Issue Date
Version
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
<Date when these changes are effective> |  |  |  |  | <List of documents which are referred in this version.>
Note on E11: *A: Add M: Modify D: Delete

## Test case List
TEST CASE LIST
Project Name |  | <Project Name>
Project Code |  | <Project Code>
Test Environment Setup Description |  | <List enviroment requires in this system 1. Server 2. Database 3. Web Browser ... >
No | Function Name | Sheet Name | Description | Pre-Condition
1 | Function A | StadiumOwner
2 | Function B | StadiumOwner
3 | Function C | Module1
4 | Function D | Module2
5 | Function E | Module2

## Field Management
Module Code | FieldManagement | [6 empty] | Pass
Test requirement | <Brief description about requirements which are tested in this sheet> | [6 empty] | Fail
Tester
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  | Untesed
15 | 0 | -2 | 0 | 11 |  |  |  | N/A
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Result | Test date | Note
View List Fields
[FieldManagement-1] | Test viewing "Quản lý sân bóng" form | 1. Login the system as Stadium Owner 2. Click "Quản lý sân bóng" tab in the menu. | The "Quản lý sân bóng" view form is displayed as list with the following informations: - "Số sân" - "Sân mẹ" - "Loại sân" - "Tình trạng hoạt động" |  | Pass | 2014-03-07
Create Field
[FieldManagement-2] | Test creating a field with blank fields | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Thêm sân" button 4. Click "Lưu" button | Error message will be displayed: - "Xin vui lòng nhập các thông tin bắt buộc". |  | Pass | 2014-03-07
[FieldManagement-3] | Test creating a field with "Số sân" is not a number | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Thêm sân" button 4. Input require information - Input "a" into "Số sân" field - Input "1" into "Sân mẹ" field - Select "11 người" in "Loại sân" field 5. Click "Lưu" button | Error message will be displayed: - "Số sân không chính xác, vui lòng nhập lại số sân". |  | Pass | 2014-03-07
[FieldManagement-4] | Test creating a field with "Số sân" is not available | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Thêm sân" button 4. Input require information - Input "1" into "Số sân" field - Input "1" into "Sân mẹ" field - Select "11 người" in "Loại sân" field 5. Click "Lưu" button | Error message will be displayed: - "Số sân đã tồn tại, xin vui lòng chọn số sân khác". |  | Pass | 2014-03-07
[FieldManagement-5] | Test creating a field with "Sân mẹ" is not existed | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Thêm sân" button 4. Input require information - Input "1" into "Số sân" field - Input "2" into "Sân mẹ" field ("2" is not existed field of this stadium in database) - Select "11 người" in "Loại sân" field 5. Click "Lưu" button | Error message will be displayed: - "Sân mẹ không tồn tại". |  | Pass | 2014-03-07
[FieldManagement-6] | Test creating a field with blank "Sân mẹ" field | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Thêm sân" button 4. Input require information - Input "1" into "Số sân" field - Blank "Sân mẹ" field - Select "11 người" in "Loại sân" field 5. Click "Lưu" button | Redirect to "Quản lý sân bóng" page with new "Sân bóng" is created |  | Pass | 2014-03-07
[FieldManagement-7] | Test creating a field with "Sân mẹ" is existed | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Thêm sân" button 4. Input require information - Input "2" into "Số sân" field - Input "1" into "Sân mẹ" field - Select "11 người" in "Loại sân" field 5. Click "Lưu" button | Redirect to "Quản lý sân bóng" page with new "Sân bóng" is created |  | Pass | 2014-03-07
Update Field
[FieldManagement-8] | Test updating a field with blank fields | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click in link named "2" in "Số sân" column 4. Blank all fields 5. Click "Lưu" button | Error message will be displayed: - "Xin vui lòng nhập các thông tin bắt buộc". |  | Pass | 2014-03-07
[FieldManagement-10] | Test updating a field with "Số sân" is not a number | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click in link named "2" in "Số sân" column 4. Input require information - Input "a" into "Số sân" field - Input "1" into "Sân mẹ" field - Select "11 người" in "Loại sân" field 5. Click "Lưu" button | Error message will be displayed: - "Số sân không chính xác, vui lòng nhập lại số sân". |  | Pass | 2014-03-07
[FieldManagement-11] | Test updating a field with "Số sân" is not available | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click in link named "2" in "Số sân" column 4. Input require information - Input "1" into "Số sân" field - Input "1" into "Sân mẹ" field - Select "11 người" in "Loại sân" field 5. Click "Lưu" button | Error message will be displayed: - "Số sân đã tồn tại, xin vui lòng chọn số sân khác". |  | Pass | 2014-03-07
[FieldManagement-9] | Test updating a field with "Sân mẹ" is not existed | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click in link named "2" in "Số sân" column 4. Change value to "3" in "Sân mẹ" field ("3" is not existed field of this stadium in database) 5. Click "Lưu" button | Error message will be displayed: - "Sân mẹ không tồn tại". |  | Pass | 2014-03-07
[FieldManagement-10] | Test updating a field with blank "Sân mẹ" field | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click in link named "2" in "Số sân" column 4. Blank "Sân mẹ" field 5. Click "Lưu" button | Redirect to "Quản lý sân bóng" page with new information of "Sân bóng" is updated |  | Pass | 2014-03-07
[FieldManagement-13] | Test updating a field with "Sân mẹ" is existed | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click in link named "2" in "Số sân" column 4. Change value to "1" in "Sân mẹ" field 5. Click "Lưu" button | Redirect to "Quản lý sân bóng" page with new information of "Sân bóng" is updated |  | Pass | 2014-03-07
Activate Field
[FieldManagement-14] | Test activating a field | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Kích hoạt" button on field numbered "2" | Reload "Quản lý sân bóng" page with field status is "Hoạt động" |  | Pass | 2014-03-07
Deactivate Field
[FieldManagement-15] | Test activating a field | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Ngừng hoạt động" button on field numbered "2" | Reload "Quản lý sân bóng" page with field status is "Ngừng hoạt động" |  | Pass | 2014-03-07
Note on F8: Pass Fail Untested N/A

## Stadium Management
Module Code | StadiumManagement | [6 empty] | Pass
Test requirement | <Brief description about requirements which are tested in this sheet> | [6 empty] | Fail
Tester
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  | Untesed
3 | 0 | 0 | 0 | 3 |  |  |  | N/A
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Result | Test date | Note
Update Stadium Profiles
[StadiumManagement-1] | Test updating stadium profile with blank fields | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Chỉnh sửa thông tin" button 4. Blank all fields 5. Click "Lưu" button | Error message will be displayed: - "Xin vui lòng nhập các thông tin bắt buộc". |  | Pass | 2014-03-07
[StadiumManagement-2] | Test updating stadium profile with wrong email format | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Chỉnh sửa thông tin" button 4. Change value to "thinhnd@" in "Email" field 5. Click "Lưu" button | Error message will be displayed: - "Email không tồn tại, vui lòng chọn email khác". |  | Pass | 2014-03-07
[StadiumManagement-3] | Test updating stadium profile with new information | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Chỉnh sửa thông tin" button 4. Change some information - change value to "thinhnd@fpt.edu.vn" in "Email" field - change value to "0982555036" in "Điện thoại" field 5. Click "Lưu" button | Redirect to "Quản lý sân bóng" page with new stadium profiles information updated |  | Pass | 2014-03-07
Note on F8: Pass Fail Untested N/A

## Promotion Management
Module Code | PromotionManagement | [6 empty] | Pass
Test requirement | <Brief description about requirements which are tested in this sheet> | [6 empty] | Fail
Tester
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  | Untesed
13 | 0 | 0 | 0 | 13 |  |  |  | N/A
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Result | Test date | Note
View List Promotions
[PromotionManagement-1] | Test viewing "Quản lý khuyến mãi" form | 1. Login the system as Stadium Staff 2. Click "Quản lý khuyến mãi" tab in the menu. | The "Quản lý khuyến mãi" view form is displayed as list with the following informations: - "Số sân" - "Thời gian khuyến mãi" - "Giảm giá" - "Tình trạng hoạt động" |  | Pass | 2014-03-07
Create Field
[PromotionManagement-2] | Test creating a promotion with blank fields | 1. Login the system as Stadium Staff 2. Go to "Quản lý khuyến mãi" page 3. Click "Thêm khuyến mãi" button 4. Click "Lưu" button | Error message will be displayed: - "Xin vui lòng nhập các thông tin bắt buộc". |  | Pass | 2014-03-07
[PromotionManagement-3] | Test creating a promotion with field not existed | 1. Login the system as Stadium Staff 2. Go to "Quản lý sân bóng" page 3. Click "Thêm sân" button 4. Input require information - Input "4" into "Số sân" field ("4" is not existed field of this stadium in database) - Input "08/03/2014" into "Thời gian bắt đầu" - Input "10/03/2014" into "Thời gian kết thúc" field - Input "10" into "Giảm giá (%)" field 5. Click "Lưu" button | Error message will be displayed: - "Sân bóng không tồn tại". |  | Pass | 2014-03-07
[PromotionManagement-4] | Test creating a promotion with "Thời gian kết thúc" is over | 1. Login the system as Stadium Staff 2. Go to "Quản lý sân bóng" page 3. Click "Thêm sân" button 4. Input require information - Input "1" into "Số sân" field - Input "05/03/2014" into "Thời gian bắt đầu" - Input "06/03/2014" into "Thời gian kết thúc" field - Input "10" into "Giảm giá (%)" field 5. Click "Lưu" button | Error message will be displayed: - "Thời gian khuyến mãi đã kết thúc, xin vui lòng chọn thời gian kết thúc khác". |  | Pass | 2014-03-07
[PromotionManagement-5] | Test creating a promotion with "Thời gian kết thúc" before "Thời gian bắt đầu" | 1. Login the system as Stadium Staff 2. Go to "Quản lý sân bóng" page 3. Click "Thêm sân" button 4. Input require information - Input "1" into "Số sân" field - Input "08/03/2014" into "Thời gian bắt đầu" - Input "06/03/2014" into "Thời gian kết thúc" field - Input "10" into "Giảm giá (%)" field 5. Click "Lưu" button | Error message will be displayed: - "Thời gian khuyến mãi không đúng, vui lòng chọn thời gian khác". |  | Pass | 2014-03-07
[PromotionManagement-6] | Test creating a promotion with "Giảm giá (%)" is not a number | 1. Login the system as Stadium Staff 2. Go to "Quản lý sân bóng" page 3. Click "Thêm sân" button 4. Input require information - Input "1" into "Số sân" field - Input "08/03/2014" into "Thời gian bắt đầu" - Input "10/03/2014" into "Thời gian kết thúc" field - Input "12a" into "Giảm giá (%)" field 5. Click "Lưu" button | Error message will be displayed: - "Giá trị giảm giá không chính xác, vui lòng nhập lại". |  | Pass | 2014-03-07
[PromotionManagement-7] | Test creating a promotion | 1. Login the system as Stadium Staff 2. Go to "Quản lý sân bóng" page 3. Click "Thêm sân" button 4. Input require information - Input "1" into "Số sân" field - Input "08/03/2014" into "Thời gian bắt đầu" - Input "10/03/2014" into "Thời gian kết thúc" field - Input "10" into "Giảm giá (%)" field 5. Click "Lưu" button | Redirect to "Quản lý khuyến mãi" page with new "Khuyến mãi" created |  | Pass | 2014-03-07
Update Field
[PromotionManagement-8] | Test updating a field with blank fields | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click in link named "2" in "Số sân" column 4. Blank all fields 5. Click "Lưu" button | Error message will be displayed: - "Xin vui lòng nhập các thông tin bắt buộc". |  | Pass | 2014-03-07
[PromotionManagement-9] | Test updating a field with parent field not existed | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click in link named "2" in "Số sân" column 4. Change value to "3" in "Sân mẹ" field ("3" is not existed field of this stadium in database) 5. Click "Lưu" button | Error message will be displayed: - "Sân mẹ không tồn tại". |  | Pass | 2014-03-07
[PromotionManagement-10] | Test updating a field with no parent field | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click in link named "2" in "Số sân" column 4. Blank "Sân mẹ" field 5. Click "Lưu" button | Redirect to "Quản lý sân bóng" page with field information updated |  | Pass | 2014-03-07
[PromotionManagement-11] | Test updating a field with parent field | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click in link named "2" in "Số sân" column 4. Change value to "1" in "Sân mẹ" field 5. Click "Lưu" button | Redirect to "Quản lý sân bóng" page with field information updated |  | Pass | 2014-03-07
Activate Field
[PromotionManagement-12] | Test activating a field | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Kích hoạt" button on field numbered "2" | Reload "Quản lý sân bóng" page with field status is "Hoạt động" |  | Pass | 2014-03-07
Deactivate Field
[PromotionManagement-13] | Test activating a field | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Ngừng hoạt động" button on field numbered "2" | Reload "Quản lý sân bóng" page with field status is "Ngừng hoạt động" |  | Pass | 2014-03-07
Note on F8: Pass Fail Untested N/A

## Reservation Management
Module Code | StadiumOwner | [6 empty] | Pass
Test requirement | <Brief description about requirements which are tested in this sheet> | [6 empty] | Fail
Tester
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  | Untesed
11 | 0 | 0 | 0 | 11 |  |  |  | N/A
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Result | Test date | Note
View List Fields
[StadiumOwner-1] | Test viewing "Field Management" form | 1. Login the system as Stadium Owner 2. Click "Quản lý sân bóng" tab in the menu. | The "Field Management" view form is displayed as list with the following informations: - Number of field - Parent field - Field type |  | Pass | 2014-03-07
Create Field
[StadiumOwner-2] | Test creating a field with blank fields | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Thêm sân" button 4. Click "Lưu" button | Error message will be displayed: - "Xin vui lòng nhập các thông tin bắt buộc". |  | Pass | 2014-03-07
[StadiumOwner-3] | Test creating a field with parent field not existed | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Thêm sân" button 4. Input require information - Input "1" into "Số sân" field - Input "2" into "Sân mẹ" field ("2" is not existed field of this stadium in database) - Input "11 người" into "Loại sân" field 5. Click "Lưu" button | Error message will be displayed: - "Sân mẹ không tồn tại". |  | Pass | 2014-03-07
[StadiumOwner-4] | Test creating a field with no parent field | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Thêm sân" button 4. Input require information - Input "1" into "Số sân" field - Blank "Sân mẹ" field - Input "11 người" into "Loại sân" field 5. Click "Lưu" button | Redirect to "Quản lý sân bóng" page with new field created |  | Pass | 2014-03-07
[StadiumOwner-5] | Test creating a field with parent field | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Thêm sân" button 4. Input require information - Input "2" into "Số sân" field - Input "1" into "Sân mẹ" field - Input "11 người" into "Loại sân" field 5. Click "Lưu" button | Redirect to "Quản lý sân bóng" page with new field created |  | Pass | 2014-03-07
Update Field
[StadiumOwner-6] | Test updating a field with blank fields | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click in link named "2" in "Số sân" column 4. Blank all fields 5. Click "Lưu" button | Error message will be displayed: - "Xin vui lòng nhập các thông tin bắt buộc". |  | Pass | 2014-03-07
[StadiumOwner-7] | Test updating a field with parent field not existed | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click in link named "2" in "Số sân" column 4. Change value to "3" in "Sân mẹ" field ("3" is not existed field of this stadium in database) 5. Click "Lưu" button | Error message will be displayed: - "Sân mẹ không tồn tại". |  | Pass | 2014-03-07
[StadiumOwner-8] | Test updating a field with no parent field | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click in link named "2" in "Số sân" column 4. Blank "Sân mẹ" field 5. Click "Lưu" button | Redirect to "Quản lý sân bóng" page with field information updated |  | Pass | 2014-03-07
[StadiumOwner-9] | Test updating a field with parent field | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click in link named "2" in "Số sân" column 4. Change value to "1" in "Sân mẹ" field 5. Click "Lưu" button | Redirect to "Quản lý sân bóng" page with field information updated |  | Pass | 2014-03-07
Activate Field
[StadiumOwner-10] | Test activating a field | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Kích hoạt" button on field numbered "2" | Reload "Quản lý sân bóng" page with field status is "Hoạt động" |  | Pass | 2014-03-07
Deactivate Field
[StadiumOwner-11] | Test activating a field | 1. Login the system as Stadium Owner 2. Go to "Quản lý sân bóng" page 3. Click "Ngừng hoạt động" button on field numbered "2" | Reload "Quản lý sân bóng" page with field status is "Ngừng hoạt động" |  | Pass | 2014-03-07
Note on F8: Pass Fail Untested N/A

## Test Report
TEST REPORT
Project Name | <Project Name> |  | Creator
Project Code | <Project Code> |  | Reviewer/Approver
Document Code | <Project Code>_Test Report_vx.x |  | Issue Date |  |  | <Date when this test report is created>
Notes | <List modules included in this release> ex: Release 1 includes 2 modules: Module1 and Module2
No | Module code | Pass | Fail | Untested | N/A | Number of test cases
1 | FieldManagement | 15 | 0 | -2 | 0 | 11
2 | StadiumManagement | 3 | 0 | 0 | 0 | 3
| Sub total | 18 | 0 | -2 | 0 | 14
| Test coverage |  | 114.2857 | %
| Test successful coverage |  | 114.2857 | %